## Test Scenarios
Project Name | hercules.works
Client | Hercules Work
Reference Document | FRS
Created By | Sahil Raju Shirale
Creation Date | 20/04/2026
Approved Date | 21/04/2026
Test Scenario ID | Reference | Test Scenarios | Priority | Number Test Cases
TS_001 | FRS | Validate the Homepage | High | 7
TS_002 | FRS | Validate the Pricing Functionality | High | 8
TS_003 | FRS | Validate the Login/Sign Up Function | HIgh | 7
TS_004 | FRS | Validate the OTP Functionality | High | 6
TS_005 | FRS | Validate the Survey Module | High | 7
TS_006 | FRS | Validate the Payment Flow | High | 10
TS_007 | FRS | Validate the Usability of the web application | Medium | 6
TS_008 | FRS | Validate the Settings | Medium | 4
|  |  | Total | 56

## HomePage
Test Scenario ID | Test Scenario | Test Case ID | Prequisites | Test Cases | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Comments
TS_001 | Validate the Homepage | TC_001 | Open the url and enter the url : https://hercules.works/ | Verify homepage Load | 1.Open URL | NA | Page loads successfully | As Expected | High | PASS
|  | TC_002 | Open the url and enter the url : https://hercules.works/ | Verify title | Check page title | NA | Title should not be empty | As Expected | Medium | PASS
|  | TC_003 | Open the url and enter the url : https://hercules.works/ | Verify Logo visibility | Observe logo | NA | Logo should be visible | As Expected | High | PASS
|  | TC_004 | Open the url and enter the url : https://hercules.works/ | Verify Navigation links | Click Pricing , Click Reaserch , Click About us | NA | Should navigate to clicked page | As Expected | High | PASS
|  | TC_005 | Open the url and enter the url : https://hercules.works/ | Scroll to bottom | Scroll page | NA | Footer content should be visible and properly loaded | As Expected | Medium | PASS
|  | TC_006 | Open the url and enter the url : https://hercules.works/ | Page load performance | Open homepage | NA | Page should load within acceptable time | As Expected | Medium | PASS
|  | TC_007 | Open the url and enter the url : https://hercules.works/ | Verify "Try Hercules Now " button | Scroll down and click on button | NA | Redirected to Login page | As Expected | Medium | PASS

## Pricing
Test Scenario ID | Test Scenario | Test Case ID | Prequisites | Test Cases | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Comments
TS_002 | Validate the Pricing Functionality | TC_008 | Open the url and enter the url : https://hercules.works/ | Open pricing page | Click Pricing | NA | Page loads successfully | As Expected | High | PASS
|  | TC_009 | Open the url and enter the url : https://hercules.works/ | Verify Starter plan | Check Starter plan | NA | Plan Should be visible | As Expected | High | PASS
|  | TC_010 | Open the url and enter the url : https://hercules.works/ | Verify Pro plan | Check Pro plan | NA | Plan Should be visible | As Expected | High | PASS
|  | TC_011 | Open the url and enter the url : https://hercules.works/ | Verify Toggle pricing | Click Annual option | NA | Plans pricing should change | As Expected | High | PASS
|  | TC_012 | Open the url and enter the url : https://hercules.works/ | Verify discount | Select annual button | NA | 20% off should display | As Expected | Medium | PASS
|  | TC_013 | Open the url and enter the url : https://hercules.works/ | Verify Plan features | Check list | NA | Features should be visible | As Expected | Medium | PASS
|  | TC_014 | Open the url and enter the url : https://hercules.works/ | Verify Get Started button | Click button | NA | Should redirect to login | As Expected | High | PASS
|  | TC_015 | Open the url and enter the url : https://hercules.works/ | Verify Multiple plans | Compare plans | NA | Plans should differ | As Expected | Medium | PASS

## Login and Sign Up
Test Scenario ID | Test Scenario | Test Case ID | Prequisites | Test Cases | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Comments
TS_003 | Validate the Login/Sign Up Function | TC_016 | Open the url and enter the url : https://hercules.works/ | Verify Open login | Click Get Started | NA | Login screen opens | As Expected | High | PASS
|  | TC_017 | Open the url and enter the url : https://hercules.works/ | Don't have account verify sign up | click on sign up | NA | Sign up screen opens | As Expected | High | PASS
|  | TC_018 | Open the url and enter the url : https://hercules.works/ | Verify valid email id and pass | Enter valid Email and pass | sahilshirale637@gmail.com pass : sahi@1705 | OTP page should pop up | As Expected | High | PASS
|  | TC_019 | Open the url and enter the url : https://hercules.works/ | Verify Wrong email id | Enter Wrong Email ID | abc @gmail.com | Error message "Please enter a valid email address" | As Expected | High | PASS
|  | TC_020 | Open the url and enter the url : https://hercules.works/ | Verify Wrong password | Enter password less than 8 character password | 123 | Err msg "Password must be at least 8 characters long" | As Expected | High | PASS
|  | TC_021 | Open the url and enter the url : https://hercules.works/ | Verify reenter password | Enter wrong pass word in reenter section | New pass : sahi@1705 , Wrong pass : 123 | Err msg "Passwords do not match" | As Expected | High | PASS
|  | TC_022 | Open the url and enter the url : https://hercules.works/ | verify terms and conditions button | Click on checkbox of terms and conditions | NA | Sign up should be clikable | As Expected | High | PASS

## OTP Validation
Test Scenario ID | Test Scenario | Test Case ID | Prequisites | Test Cases | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Comments
TS_004 | Validate the OTP Functionality | TC_023 | Open the url and enter the url : https://hercules.works/ | Verify OTP screen load | After login or sign up | NA | OTP screen visible | As Expected | High | PASS
|  | TC_024 | Open the url and enter the url : https://hercules.works/ | Verify Valid OTP | Enter 6 digits | 123456 | Accept OTP | As Expected | High | PASS
|  | TC_025 | Open the url and enter the url : https://hercules.works/ | Verify Invalid OTP | Enter wrong OTP | 12456 | Error message | As Expected | High | PASS
|  | TC_026 | Open the url and enter the url : https://hercules.works/ | Verify Short OTP | Click Enter 3 digits , | 123 | Shouldverify OTP button not clickable | As Expected | High | PASS
|  | TC_027 | Open the url and enter the url : https://hercules.works/ | Verify Empty OTP | Submit blank | Blank | Shouldverify OTP button not clickable | As Expected | High | PASS
|  | TC_028 | Open the url and enter the url : https://hercules.works/ | Verify Non-numeric OTP | Enter letters | abcefg | Should not accept | As Expected | Medium | PASS

## Usability
Test Scenario ID | Test Scenario | Test Case ID | Prequisites | Test Cases | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Comments
TS_007 | Validate the Usability of the web application | TC_046 | Open the url and enter the url : https://hercules.works/ | Verify Button hover | Hover buttons | NA | Style change | As Expected | Low | PASS
|  | TC_047 | Open the url and enter the url : https://hercules.works/ | Verify Scroll behavior without login | Scrolldown | NA | Scroll smoothly | stops in between at "prediction engine " feels slow and laggy | Low | Fail
|  | TC_048 | Open the url and enter the url : https://hercules.works/ | Verify Font consistency | Check font | NA | Consistent UI | As Expected | Low | PASS
|  | TC_050 | Open the url and enter the url : https://hercules.works/ | Verify Alignment | Check layout | NA | Proper alignment | As Expected | Medium | PASS
|  | TC_051 | Open the url and enter the url : https://hercules.works/ | Verify Error message UI | Trigger error | NA | Should display clearly | As Expected | Medium | PASS
|  | TC_052 | Open the url and enter the url : https://hercules.works/ | Verify Mobile View | Open in mobile | NA | UI responsive | As Expected | Medium | PASS

## Survey Module
Test Scenario ID | Test Scenario | Test Case ID | Prequisites | Test Cases | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Comments
TS_005 | Validate the Survey Module | TC_029 | Open the url and enter the url : https://hercules.works/ | Verify Open survey page | Navigate to survey page | NA | Page loads successfully | As Expected | High | PASS
|  | TC_030 | Open the url and enter the url : https://hercules.works/ | Verify List surveys | Check list | NA | Surveys visible | As Expected | Medium | PASS
|  | TC_031 | Open the url and enter the url : https://hercules.works/ | Verify Create survey | Enter prompt | Prompt | Survey created | As Expected | High | PASS
|  | TC_032 | Open the url and enter the url : https://hercules.works/ | Empty prompt | Submit empty | NA | Submit option lshould not visible | As Expected | Medium | PASS
|  | TC_033 | Open the url and enter the url : https://hercules.works/ | verify Add question | Type question and submit | quesations | Question added | As Expected | High | PASS
|  | TC_034 | Open the url and enter the url : https://hercules.works/ | Verify edit question | Give prompt to edit the queation | prompt | Should update | As Expected | High | PASS
|  | TC_035 | Open the url and enter the url : https://hercules.works/ | Verify "Delete question | Give prompt to delete the queation | prompt | Question removed | As Expected | Medium | PASS

## Payment Flow
Test Scenario ID | Test Scenario | Test Case ID | Prequisites | Test Cases | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Comments
TS_006 | Validate the Payment Flow | TC_036 | Open the url and enter the url : https://hercules.works/ | Verify Open payment oprtion | select plan , click on upgrade plan | NA | Payment page load | As Expected | High | PASS
|  | TC_037 | Open the url and enter the url : https://hercules.works/ | Verify using mobile number payment | enter mobile number and click on submit | 8928352878 | Title should not be mobile number should save | As Expected | High | PASS
|  | TC_038 | Open the url and enter the url : https://hercules.works/ | Verify empty mobile number | empty | NA | err msg " entyer your mobile number " | As Expected | High | PASS
|  | TC_039 | Open the url and enter the url : https://hercules.works/ | Verify payment UPI | click on UPI option | NA | Should reflect scaner code and all UPI apps options | As Expected | High | PASS
|  | TC_040 | Open the url and enter the url : https://hercules.works/ | Verify payment EMI | Click on EMI | NA | Should reflect credit card and all payment options | As Expected | High | PASS
|  | TC_041 | Open the url and enter the url : https://hercules.works/ | Verify payment Netbanking | Click on net banking | NA | Should reflect all banks option | As Expected | High | PASS
|  | TC_042 | Open the url and enter the url : https://hercules.works/ | Verify wallet payment | Click on wallet , Choose Mobikwik | NA | Option selected | As Expected | High | PASS
|  | TC_043 | Open the url and enter the url : https://hercules.works/ | Verify Enter OTP | Enter 123456 | NA | OTP accepted | As Expected | High | PASS
|  | TC_044 | Open the url and enter the url : https://hercules.works/ | Verify Invalid OTP | Enter wrong OTP | NA | Error shown | As Expected | High | PASS
|  | TC_045 | Open the url and enter the url : https://hercules.works/ | Verify Exit payment | Click exit | NA | Exit confirmed | As Expected | Medium | PASS

## Settings
Test Scenario ID | Test Scenario | Test Case ID | Prequisites | Test Cases | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Comments
TS_008 | Validate the Settings | TC_053 | Open the url and enter the url : https://hercules.works/ | Verify Open Settings page | Click on Settings option | NA | Settings page should load successfully | As Expected | High | PASS
|  | TC_054 | Open the url and enter the url : https://hercules.works/ | Verify Update account details | Modify profile info Name and all details | NA | Changes should be saved successfully | stops in between at "prediction engine " feels slow and laggy | High | PASS
|  | TC_055 | Open the url and enter the url : https://hercules.works/ | Verify Invalid input validation | Enter invalid data (empty/incorrect format) | NA | Proper error message should be displayed | Old saved details are showing | Low | Fail
|  | TC_056 | Open the url and enter the url : https://hercules.works/ | Verify Navigation back | Click back or home from settings | NA | User should be redirected correctly | As Expected | Medium | PASS